## Sheet1
ACG - Autopilot AADJ Implementation Plan
Phase | Action Items | Description | Estimated Timelines | Percentage Completed | Owner | Comments | Date
Prepare | Prepare Your Environment | Ensure you have an active Azure AD subscription and access to Microsoft Intune | 1 Hour |  |  |  | 7th August 2023
|  | Verify that you meet the prerequisites for Autopilot, including supported Windows versions and hardware | 1 Hour |  |  |  | 7th August 2023
|  | Assign necessary permissions to Intune administrators for device enrollment and management | 1 Day |  |  |  | 7th August 2023
Configure | Configure Autopilot Deployment | Create an Autopilot deployment profile in the Microsoft Endpoint Manager admin center | 1 Day |  |  |  | 18th August 2023
|  | Define OOBE settings, language, region, keyboard settings, and other customization options | 1 Hour |  |  |  | 18th August 2023
Choose whether to skip specific screens during setup, such as privacy settings and EULA acceptance.
Register | Register Devices with Autopilot | Obtain hardware hashes for devices to be enrolled in Autopilot | 2 Hours |  |  |  | 18th August 2023
|  | Upload hardware hashes to the Autopilot service in the Microsoft Endpoint Manager admin center | 1 Hour |  |  |  | 18th August 2023
Assign | Assign Licenses and Profiles | Ensure user accounts have required licenses (e.g., Microsoft 365, Intune) | 2 Hour |  |  |  | 19th August onwards
Configure Intune profiles and policies for Autopilot-enrolled devices
Test | Test Autopilot Deployment | Perform a pilot deployment to a small group of test devices | 1 Hour |  |  |  | 7th August 2023
|  | Verify the deployment profile and settings during the OOBE process | 1 Hour |  |  |  | 7th August 2023
Communicate | Communicate with Users | Inform users about the upcoming Autopilot deployment and its benefits | 1 Hour |  |  |  | 7th August 2023
|  | Provide clear instructions on the enrollment process and any user actions required. | 1 Hour |  |  |  | 7th August 2023
Deploy | Deploy Autopilot at Scale | Deploy Autopilot to all targeted devices | 1 Hour |  |  |  | 7th August 2023
|  | Ensure devices have internet connectivity during initial setup | 1 Hour |  |  |  | 7th August 2023
Monitor | Monitor and Manage Devices | Regularly review Intune console to monitor device compliance and resolve issues | 1 Hour |  |  |  | 7th August 2023
|  | Utilize Intune reporting and analytics for insights into device status and usage. | 1 Hour |  |  |  | 7th August 2023
Support | Provide Ongoing Support | Offer ongoing support to end-users with questions or issues | 1 Hour |  |  |  | 7th August 2023
|  | Keep documentation up-to-date and provide self-help resources | 1 Hour |  |  |  | 7th August 2023