## SCCM to Intune
SCJ - SCCM to Intune Migration Plan (For HAADJ & AADJ)
Phase | Action Items | Description | Estimated Timelines | Percentage Completed | Owner | Comments | Date
Initiation | Define Migration Goals and Scope | Hold a kickoff meeting with stakeholders to discuss the migration objectives and define the scope | 1 Hour |  |  |  | 17th August 2023
|  | Document the desired outcomes and key performance indicators (KPIs) for the Intune migration | 1 Hour |  |  |  | 17th August 2023
|  | Define which devices and user groups will be included in the initial migration | 1 Day |  |  |  | 17th August 2023
| Familiarize Yourself with Intune | Assemble the project team and provide training sessions to introduce Intune capabilities | 1 Hour |  |  |  | 17th August 2023
|  | Review Microsoft documentation and best practices for Intune | 1 Day |  |  |  | 17th August 2023
|  | Identify potential challenges and plan mitigation strategies | 1 Hour |  |  |  | 17th August 2023
Planning | Set Up Intune Environment | Create an Intune tenant and configure general settings, such as tenant name, region, and language | 1 Day |  |  |  | 18th August 2023
|  | Integrate Intune with Azure AD to enable user and device synchronization | 1 Hour |  |  |  | 18th August 2023
Configure compliance settings and enroll Intune-managed devices into Intune
|  | Set up role-based access control (RBAC) for managing Intune permissions |  |  |  |  | 18th August 2023
| Plan for CoExistence | Determine the duration of the co-existence phase and which devices will be managed by SCCM or Intune | 4 Hours |  |  |  | 18th August 2023
|  | Define communication strategies to inform users about the migration process |  |  |  |  | 18th August 2023
Analysis | Assess Your Environment | Inventory all SCCM-managed devices and applications | 2 Hours |  |  |  | 18th August 2023
|  | Identify dependencies and interconnections between SCCM components | 1 Hour |  |  |  | 18th August 2023
|  | Review existing SCCM collections, compliance policies, and configuration baselines | 1 Hour |  |  |  | 18th August 2023
| Prepare Devices for Migration | Ensure all devices meet the prerequisites for Intune enrollment and compliance | 2 -3 Days |  |  |  | 19th August onwards
|  | Uninstall SCCM client from devices that will be fully migrated to Intune | 2 Hour |  |  |  | 19th August onwards
Design | Data Migration | Plan and execute the migration of application packages from SCCM to Intune | 2 Hour |  |  |  | 19th August onwards
Migrate device collections, configuration items, and compliance policies to Intune
|  | Repackage applications as needed to ensure compatibility with Intune deployment methods | 30 Mins |  |  |  | 19th August onwards
Decide on the method of application deployment (Microsoft Store, Win32 apps, etc.)
| Application Deployment | Package and deploy applications using Intune
|  | Test application deployments on a limited set of devices to validate success | 2 Hour |  |  |  | 19th August onwards
Implementation | Device Enrollment | Enroll devices into Intune using Azure AD join or other appropriate methods | 1 Hour |  |  |  | 17th August 2023
|  | Configure enrollment settings and Intune Company Portal for self-enrollment | 1 Hour |  |  |  | 17th August 2023
| Policy and Configuration Migration | Recreate SCCM policies, profiles, and configurations in Intune | 1 Hour |  |  |  | 17th August 2023
|  | Create compliance policies, configuration profiles, VPN settings, Wi-Fi settings, etc | 1 Day |  |  |  | 17th August 2023
Testing | Testing and Pilot Deployment | Conduct comprehensive testing of the Intune deployment in a pilot group | 1 Hour |  |  |  | 17th August 2023
|  | Gather feedback from pilot users and address any issues or concerns | 1 Hour |  |  |  | 17th August 2023
Deployment | Full Deployment | Roll out Intune to all targeted devices and user groups | 1 Hour |  |  |  | 17th August 2023
|  | Monitor the migration progress and resolve any migration-related issues | 1 Hour |  |  |  | 17th August 2023
Closure | User Training and Support | Provide training sessions and documentation to help users adapt to Intune | 1 Hour |  |  |  | 17th August 2023
|  | Offer ongoing support for users experiencing any post-migration issues | 1 Hour |  |  |  | 17th August 2023
| Decommission SCCM (Optional) | Assess whether SCCM can be decommissioned based on successful Intune adoption | 1 Hour |  |  |  | 17th August 2023
|  | Plan for data migration or archival if required | 1 Day |  |  |  | 17th August 2023
Evaluate the success of the migration against predefined goals and KPIs
| Post-Migration Evaluation | Conduct a post-migration survey to gather feedback from end-users | 2 Hours |  |  |  | 17th August 2023